## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group H | Completed | 15
Project title | SupaClean laundry and dry cleaning management system | In Progress | 3
Stakeholder or organisation | SupaClean | Not Started | 0
Group mentor |  | Delayed | 1
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | In Progress | Overdue | 0
Overall status | In Progress
Overall % complete | Stakeholder engagement, requirements gathering, feasibility/risk planning and Phase 1 project scheduling have been allocated across the 10-member group. | Contribution Summary | Count
Main achievement | Final consolidation, evidence verification, group reflection and confirmation of individual completion records. | Contribution entries | 47
Main challenge | Review and verify all Phase 1 documents, then finalise the Unit 1 submission. | Verified entries | 47
Next planned activity |  | Unverified entries | 0
|  | Stakeholder engagements | 1

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Masendeke CP; Mahlangu P | Tue 8/18/26 | Wed 8/19/26 | Completed | 100 |  | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Masendeke CP; Mahlangu P | Tue 8/18/26 |  | Completed | 100 |  | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Masendeke CP; Mahlangu P | Thu 8/20/26 | Sat 8/22/26 | Completed | 100 |  | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Masendeke CP; Mahlangu P; Leeu FD; Maema KE | Tue 8/18/26 | Wed 8/19/26 | Completed | 100 |  | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Masendeke CP; Mahlangu P; Leeu FD; Maema KE | Tue 8/18/26 | Wed 8/19/26 | Completed | 100 |  | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Leeu FD; Maema KE | Sat 8/22/26 | 29/8/2026 | In Progress | 100 |  | Yes |  | On Track
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Dasheka T; Ntlati TT | Thu 8/27/26 | 29/8/2026 | Completed | 100 | https://cutfs-my.sharepoint.com/personal/224081629_stud_cut_ac_za/Documents/Documents/FreshnClean_ITC327W_Project_Progress_Tracker_Phase1.xlsx!Task%20Progress!AutoShape%204 | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Maema KE | Thu 8/27/26 | Tue 8/25/26 | Completed | 100 | https://eur02.safelinks.protection.outlook.com/?url=https%3A%2F%2Fgithub.com%2FMaema-kat%2FSupaClean-Dry-Clean-System-WIL-.git&data=05%7C02%7C224079714%40stud.cut.ac.za%7C64968eb4a5654296277d08df061ba4b6%7Cb940c14991b74bcfba2c0db8d817196d%7C0%7C0%7C639236387959627963%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=R6w8pdgcH1aIpo%2BOg9841qMGRH%2ByfwRRBH0Bt31sm9s%3D&reserved=0 | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | TBC |  |  | Delayed | 0 |  | No |  | Delayed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Dasheka T; Ntlati TT | Fri 8/28/26 | Mon 8/31/26 | In Progress | 100 | https://cutfs-my.sharepoint.com/personal/224081629_stud_cut_ac_za/Documents/Documents/FreshnClean_ITC327W_Project_Progress_Tracker_Phase1.xlsx!Task%20Progress!AutoShape%204 | Yes |  | On Track
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All 10 group members | Tue 8/11/26 | Fri 8/14/26 | Completed | 100 |  | Yes |  | Completed
U1-12 | Unit 1 / Phase 1 | Activity 1.1 | Project kickoff meeting | Dasheka T; Leeu FD; Maema KE; Maleke KT; Masendeke CP; Mahlangu P; Mojakwe KB; Moretlwe RK; Ntlati TT; Stallenberg BC | Tue 8/18/26 | Tue 8/18/26 | Completed | 100 |  | Yes |  | Completed
U1-13 | Unit 1 / Phase 1 | Activity 1.1 | Gather functional requirements | Leeu FD; Maema KE | Mon 8/24/26 | Tue 8/25/26 | Completed | 100 |  | Yes |  | Completed
U1-14 | Unit 1 / Phase 1 | Activity 1.1 | Gather non-functional requirements | Leeu FD; Maema KE | Wed 8/26/26 | Thu 8/27/26 | Completed | 100 |  | Yes |  | Completed
U1-15 | Unit 1 / Phase 1 | Activity 1.3 | Technical feasibility | Maleke KT; Moretlwe RK | Sat 8/22/26 | Sat 8/22/26 | Completed | 100 |  | Yes |  | Completed
U1-16 | Unit 1 / Phase 1 | Activity 1.3 | Economical feasibility | Maema KT; Moretlwe RK | Tue 8/25/26 | Tue 8/25/26 | Completed | 100 |  | Yes |  | Completed
U1-17 | Unit 1 / Phase 1 | Activity 1.3 | Create project risk register | Mojakwe KB; Stallenberg BC | Tue 8/25/26 | Wed 8/26/26 | In Progress | 50 |  | Yes |  | On Track
U1-18 | Unit 1 / Phase 1 | Activity 1.3 | Risk review meeting | Mojakwe KB; Stallenberg BC | Thu 8/27/26 | Thu 8/27/26 | Completed | 100 |  | Yes |  | Completed
U1-19 | Unit 1 / Phase 1 | Activity 1.3 | Review all Phase 1 documents | Dasheka T; Leeu FD; Maema KE; Maleke KT; Masendeke CP; Mahlangu P; Mojakwe KB; Moretlwe RK; Ntlati TT; Stallenberg BC | Sat 8/29/26 | Mon 8/31/26 | Completed | 100 |  | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Dasheka T | 219007064 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Leeu FD | 223044569 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Maema KE | 224079714 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Maleke KT | 222009259 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Masendeke CP | 224043099 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Mhlangu P |  | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Mojakwe KB | 223032987 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Moretlwe RK | 221012635 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Ntlati TT | 224081629 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Stallenberg BC | 224081442 | Unit 1 / Phase 1 | Project kickoff meeting | Project kickoff meeting | Participated in the project kickoff meeting and contributed to the initial discussion of the project scope, objectives and responsibilities. | Tue 8/18/26 | 3 |  | Yes | 2026-08-19 | Team alignment achieved on the high-level roadmap, SRS scope, and communication protocols established during the session.
Masendeke CP | 224043099 | Unit 1 / Phase 1 | Identify stakeholder & organization | Identify stakeholder & organization | Assisted with identifying and documenting the stakeholder, organisation and relevant business context. | 2026-08-29 | 5 |  | Yes | 2026-08-19 | Special focus placed on resource owners and cross-functional team leads flagged in recent schedule updates.
Mhlangu P |  | Unit 1 / Phase 1 | Identify stakeholder & organization | Identify stakeholder & organization | TBC – confirm personally completed work and evidence | 2026-08-29 | 5 |  | Yes | 2026-08-19 | Special focus placed on resource owners and cross-functional team leads flagged in recent schedule updates.
Masendeke CP | 224043099 | Unit 1 / Phase 1 | Stakeholder interviews/meeting | Stakeholder interviews/meeting | Participated in the stakeholder meeting and contributed questions and observations regarding the current business process and system requirements. | 2026-08-29 | 3 |  | Yes | 2026-08-19 | Primary objective is to secure sign-off on the baseline timeline and confirm mitigation ownership for high-priority risks.
Mhlangu P |  | Unit 1 / Phase 1 | Stakeholder interviews/meeting | Stakeholder interviews/meeting | TBC – confirm personally completed work and evidence | 2026-08-29 | 3 |  | Yes | 2026-08-19 | Primary objective is to secure sign-off on the baseline timeline and confirm mitigation ownership for high-priority risks.
Leeu FD | 223044569 | Unit 1 / Phase 1 | Stakeholder interviews/meeting | Stakeholder interviews/meeting | TBC – confirm personally completed work and evidence | 2026-08-29 | 3 |  | Yes | 2026-08-19 | Primary objective is to secure sign-off on the baseline timeline and confirm mitigation ownership for high-priority risks.
Maema KE | 224079714 | Unit 1 / Phase 1 | Stakeholder interviews/meeting | Stakeholder interviews/meeting | TBC – confirm personally completed work and evidence | 2026-08-29 | 3 |  | Yes | 2026-08-19 | Primary objective is to secure sign-off on the baseline timeline and confirm mitigation ownership for high-priority risks.
Masendeke CP | 224043099 | Unit 1 / Phase 1 | Problem analysis & evidence collection | Problem analysis & evidence collection | Assisted with analysing the current process and collecting evidence of the stakeholder's identified problems and needs. | 2026-08-29 | 2 |  | Yes | 2026-08-19
Mhlangu P |  | Unit 1 / Phase 1 | Problem analysis & evidence collection | Problem analysis & evidence collection | TBC – confirm personally completed work and evidence | 2026-08-29 | 2 |  | Yes | 2026-08-19
Leeu FD | 223044569 | Unit 1 / Phase 1 | Gather functional requirements | Gather functional requirements | Assisted with refining and documenting the functional requirements for the proposed system. | 2026-08-29 | 2 |  | Yes | 2026-08-19 | All identified features align directly with the business goals approved in the operational feasibility study.
Maema KE | 224079714 | Unit 1 / Phase 1 | Gather functional requirements | Gather functional requirements | Identified and documented functional requirements based on the stakeholder's needs and current business process. | 2026-08-29 | 2 |  | Yes | 2026-08-19 | All identified features align directly with the business goals approved in the operational feasibility study.
Leeu FD | 223044569 | Unit 1 / Phase 1 | Gather non-functional requirements | Gather non-functional requirements | Assisted with reviewing and documenting the non-functional requirements to ensure they were relevant to the proposed solution. | 2026-08-29 | 1.5 |  | Yes | 2026-08-19 | Established clear benchmarks (e.g., page load times, uptime targets, data encryption standards) that the engineering team must meet.
Maema KE | 224079714 | Unit 1 / Phase 1 | Gather non-functional requirements | Gather non-functional requirements | Identified relevant non-functional requirements relating to usability, performance, security, availability and system quality. | 2026-08-29 | 1.5 |  | Yes | 2026-08-19 | Established clear benchmarks (e.g., page load times, uptime targets, data encryption standards) that the engineering team must meet.
Leeu FD | 223044569 | Unit 1 / Phase 1 | Write software requirements specification | Write software requirements specification | Assisted with compiling and reviewing the Software Requirements Specification, including requirements, scope and integration considerations. | 2026-08-29 | 4 |  | Yes | 2026-08-19 | Ensured all technical specifications map directly to the approved MS Project schedule milestones and risk mitigation boundaries.
Maema KE | 224079714 | Unit 1 / Phase 1 | Write software requirements specification | Write software requirements specification | Drafted and refined sections of the Software Requirements Specification based on the stakeholder analysis and requirements gathered. | 2026-08-29 | 4 |  | Yes | 2026-08-19 | Ensured all technical specifications map directly to the approved MS Project schedule milestones and risk mitigation boundaries.
Maleke KT | 222009259 | Unit 1 / Phase 1 | Technical feasibility | Technical feasibility | Evaluated the technical feasibility of the proposed solution, including the technologies, integration requirements and available technical skills. | 2026-08-29 | 3 |  | Yes | 2026-08-19 | Confirmed that the technologies required for the SRS implementation are viable and sustainable within our current tech stack.
Moretlwe RK | 221012635 | Unit 1 / Phase 1 | Technical feasibility | Technical feasibility | Assisted with assessing the technical requirements, technology constraints and integration feasibility of the proposed system. | 2026-08-29 | 3 |  | Yes | 2026-08-19 | Confirmed that the technologies required for the SRS implementation are viable and sustainable within our current tech stack.
Maema KT | 224079714 | Unit 1 / Phase 1 | Economical feasibility | Economical feasibility | TBC – confirm personally completed work and evidence | 2026-08-29 | 3 |  | Yes | 2026-08-19 | The financial projections confirm the project is cost-effective and fits within the designated corporate budget allocations.
Moretlwe RK | 221012635 | Unit 1 / Phase 1 | Economical feasibility | Economical feasibility | Assisted with assessing the economic feasibility of the project and the resources required for development. | 2026-08-29 | 3 |  | Yes | 2026-08-19 | The financial projections confirm the project is cost-effective and fits within the designated corporate budget allocations.
Mojakwe KB | 223032987 | Unit 1 / Phase 1 | Create project risk register | Create project risk register | Identified project risks and documented their categories, likelihood, impact, risk scores, mitigation actions and owners. | 2026-08-29 | 4.5 |  | Yes | 2026-08-19 | Highlighting critical path dependencies that pose the highest threat to the baseline timeline.
Stallenberg BC | 224081442 | Unit 1 / Phase 1 | Create project risk register | Create project risk register | Assisted with developing the project risk register and documenting appropriate mitigation and contingency actions. | 2026-08-29 | 4.5 |  | Yes | 2026-08-19 | Highlighting critical path dependencies that pose the highest threat to the baseline timeline.
Mojakwe KB | 223032987 | Unit 1 / Phase 1 | Risk review meeting | Risk review meeting | Participated in the risk review meeting and contributed to the identification, assessment and prioritisation of project risks. | 2026-08-29 | 3 |  | Yes | 2026-08-19 | Highlighting critical path dependencies that pose the highest threat to the baseline timeline.
Stallenberg BC | 224081442 | Unit 1 / Phase 1 | Risk review meeting | Risk review meeting | Participated in the risk review and assisted with reviewing risk status, mitigation actions and the highest-priority project risks. | 2026-08-29 | 3 |  | Yes | 2026-08-19 | Highlighting critical path dependencies that pose the highest threat to the baseline timeline.
Dasheka T | 219007064 | Unit 1 / Phase 1 | Create Microsoft Project schedule | Create Microsoft Project schedule | Created and updated project activities, durations, dates, dependencies, responsibilities and milestones in Microsoft Project. | 2026-08-29 | 3.5 | https://cutfs-my.sharepoint.com/personal/224081629_stud_cut_ac_za/Documents/Documents/FreshnClean_ITC327W_Project_Progress_Tracker_Phase1.xlsx!Task%20Progress!AutoShape%204 | Yes | 2026-08-19 | Ready to transition from planning to active tracking.
Ntlati TT | 224081629 | Unit 1 / Phase 1 | Create Microsoft Project schedule | Create Microsoft Project schedule | Assisted with developing and reviewing the Microsoft Project schedule to ensure the Phase 1 activities reflected the actual project progress. | 2026-08-29 | 3.5 | https://cutfs-my.sharepoint.com/personal/224081629_stud_cut_ac_za/Documents/Documents/FreshnClean_ITC327W_Project_Progress_Tracker_Phase1.xlsx!Task%20Progress!AutoShape%204 | Yes | 2026-08-19 | Ready to transition from planning to active tracking.
Maema KE | 224079714 | Unit 1 / Phase 1 | Create GitHub repository & README | Create GitHub repository & README | Contributed to setting up and reviewing the GitHub repository and README and ensuring the project documentation was organised. |  | 3 | https://eur02.safelinks.protection.outlook.com/?url=https%3A%2F%2Fgithub.com%2FMaema-kat%2FSupaClean-Dry-Clean-System-WIL-.git&data=05%7C02%7C224079714%40stud.cut.ac.za%7C64968eb4a5654296277d08df061ba4b6%7Cb940c14991b74bcfba2c0db8d817196d%7C0%7C0%7C639236387959627963%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=R6w8pdgcH1aIpo%2BOg9841qMGRH%2ByfwRRBH0Bt31sm9s%3D&reserved=0 | Yes | 2026-08-19 | Ensured the README includes clear setup instructions, project architecture notes, and a high-level timeline linking back to our master milestones.
Dasheka T | 219007064 | Unit 1 / Phase 1 | Progress tracker | Progress tracker | Reviewed and contributed to updating the project progress tracker to ensure activities and individual contributions were accurately recorded. |  | 4 |  | Yes | 2026-08-19 | All current metrics are live and reflect accurate project health.
Ntlati TT | 224081629 | Unit 1 / Phase 1 | Progress tracker | Progress tracker | Reviewed and contributed to updating the project progress tracker to ensure activities and individual contributions were accurately recorded. |  | 4 |  | Yes | 2026-08-19 | All current metrics are live and reflect accurate project health.
Dasheka T | 219007064 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Leeu FD | 223044569 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Maema KE | 224079714 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Maleke KT | 222009259 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Masendeke CP | 224043099 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Mhlangu P |  | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Mojakwe KB | 223032987 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Moretlwe RK | 221012635 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Ntlati TT | 224081629 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.
Stallenberg BC | 224081442 | Unit 1 / Phase 1 | Review all Phase 1 documents | Review all Phase 1 documents | Reviewed the Phase 1 documents for completeness, consistency and alignment with the project requirements. |  | 3.5 |  | Yes | 2026-08-19 | This comprehensive review ensures absolute alignment between business expectations, technical constraints, and the development timeline before transition to Phase 2.

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-19 | Unit 1 / Phase 1 | Stakeholder meeting/interview | Understand FreshnClean's current process, problems, requirements and proposed digital solution. | Masendeke CP; Mahlangu P; Leeu FD; Maema KE | SupaClean Manager | Clarified the laundry/dry-cleaning workflow, customer order process, pickup/drop-off points, central processing, order status/collection, operational roles and existing ticket/docket process. | Confirm outstanding details including ticket/docket integration, referral/discount rules, final pickup/drop-off details and exceptional garment notification procedures. | #VALUE!
#VALUE!
#VALUE!
#VALUE!

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-18 | Unit 1 / Phase 1 | Could not identify stakeholder | Going broader to other places or busy businesses places to identify more businesses | Manage to go to placess with more stores/businesses and quickly found potential stakeholder | Masendeke CP; Mahlangu P |  | Resolved
2026-08-27 | Unit 1 / Phase 1 | Some requirements still require stakeholder confirmation. | Could delay finalisation of parts of the SRS and system design. | Record the outstanding items and confirm them with the stakeholder before final design approval. | All 10 group members |  | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | In Progress
Reporting period | 18 August 2026 – 31 August 2026 | Progress report updated | In Progress
Overall phase status | In Progress | Individual contributions recorded | Yes
What was completed during this phase? | The group completed stakeholder engagement and developed the initial understanding of the FreshnClean problem, requirements, feasibility, risks and project structure. Responsibilities were allocated across the 10 group members, including Microsoft Project, GitHub and the Progress Tracker. | Stakeholder engagement recorded | Yes
What remains incomplete? | Final document review, evidence verification, individual contribution confirmation, group reflection and any outstanding stakeholder clarifications remain. | Challenges and actions updated | Yes
Why is it incomplete? | Some requirements still need confirmation, and the group must verify that all Phase 1 artefacts agree with the actual work completed by each member. | Group reflection completed | Yes
Which contributions were particularly important? | Stakeholder engagement and requirements work were particularly important, together with the Microsoft Project schedule, risk register, SRS and evidence/document review. | Microsoft Project updated | Yes
Were there participation concerns? | TBC – confirm any participation concerns using the group's actual contribution evidence. | GitHub evidence available | TBC
What will the group improve in the next phase? | Use clearer task ownership and earlier coordination in Phase 2, while keeping the SRS, Microsoft Project, Progress Tracker, GitHub and stakeholder evidence aligned. | Confidential peer check completed | TBC
Main priority for the next phase | Complete Phase 1 document review and evidence verification, then move into system architecture and design.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | FreshnClean | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The main learning from Phase 1 was the importance of understanding the stakeholder's real operational workflow before designing the system. The group identified the customer journey, pickup/drop-off process, processing workflow, order status and key system requirements. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Stakeholder engagement and requirements gathering established a clearer project direction. The group also divided Phase 1 responsibilities across the 10 members.Thorough Feasibility Alignment: Separating the operational, technical, and economic feasibility studies provided a rock-solid business case and prevented early scope creep.Proactive Stakeholder Engagement: Identifying and mapping key stakeholders right after the MS Project plan baseline ensured high attendance and valuable input during the kick-off meeting.Strong Technical Foundation: Initializing the GitHub repository early and embedding the SRS benchmarks directly into the README.md gave the development team immediate clarity on technical constraints. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The group still needs to confirm several stakeholder details and ensure that the SRS, Microsoft Project, Progress Tracker, GitHub evidence and individual contribution records all agree.Timeline Estimation Discrepancy: The gathering of functional and non-functional requirements took 20% longer than initially estimated in the MS Project plan due to conflicting stakeholder feedback.Review Bottlenecks: Reviewing every single document at the end of Phase 1 created a documentation bottleneck, delaying the final sign-off by several days | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Work was divided across stakeholder analysis, requirements, feasibility, risk management, Microsoft Project, GitHub and progress tracking. The final Phase 1 document review is assigned to everyone.
Did all members contribute fairly? Explain. | Yes everyone managed to do the parts assigned to them by the group and its fair because the group did not appose to any of the way the work was divided
How did the group handle disagreements or delays? | The group used task allocation and follow-up review to manage work. Any delays or disagreements should be recorded in the Challenges & Actions sheet rather than assumed.
What did the group learn from the stakeholder? | The stakeholder clarified the current laundry/dry-cleaning workflow, customer process, pickup/drop-off points, operational roles, order status and the existing ticket/docket process.
Improvement action 1 for the next phase | Assign Phase 2 responsibilities before design work begins and confirm each member's deliverables.
Improvement action 2 for the next phase | Use a shared evidence/checking process so that the SRS, MPP, GitHub and Progress Tracker remain consistent.
Priority for the next phase | Complete Phase 1 document review and evidence verification, then begin system architecture and design.